## Decision register
Scope | Decision | Decide when | Proposed owner | Evidence needed | Reference | Status
Portfolio | Nominate Infra offering sponsor and tower leads with committed validation effort | Now | CIS Infra leadership | Named people and effort | GTM proposal V3 | Open
Portfolio | Approve a 30-day validation of the portfolio | Now | CIS Infra leadership | This portfolio | GTM proposal V3 | Open
Portfolio | Approve tower attribution, shared cost treatment and margin definitions before any quote | Finance approval | Finance | Internal costing model | R2 in each deck | Open
Portfolio | Approve sell rates for CIS Infra and specialist towers | Finance approval | Finance | Rate cards | C1 in each deck | Open
Portfolio | Sign internal support agreements with Security, DevOps, AI, Data, Data Engineering | Tower agreement | Tower leads | Signed agreements | 05 A12 | Open
Portfolio | Confirm approved branding, Gellix font use and Microsoft alliance positioning | Before external use | Marketing and alliance owner | Brand approval | All decks | Open
Portfolio | Validate every RACI row with tower leads | Tower agreement | Integrated service owner | Workshop | R1 in each deck | Open
01 Landing Zone | Adopt assess, extend, establish routes and scope boundaries | Now | Offering owner | Deck 01 | 01 exec 7 | Open
01 Landing Zone | Terraform ownership: DevOps or CIS Infra | Now | CIS Infra and DevOps leads | Who staffs modules | 01 D1 | Open
01 Landing Zone | Reference estimate for extension (replace 88 role-day illustration) | After pilot | Integrated service owner | Pilot effort | 01 A2 | Open
01 Landing Zone | Approved demonstration environment and IaC assets | After pilot | CIS Infra | Working deployment | 01 D1 | Open
02 Agent Governance | Pilot agent cohort and runtimes | Now | AI platform leader | Agent list | 02 D1 | Open
02 Agent Governance | Containment and restart authority (per customer) | Per engagement | Customer risk owner | Named roles | 02 D1 | Open
02 Agent Governance | Dormancy threshold and exceptions | After pilot | Customer service owner | Usage patterns | 02 A5 | Open
02 Agent Governance | Stop-time targets per runtime | After drills | Integrated service owner | Measured drills | 02 K4 | Open
03 Gateway | Production on GA tiers; AI Gateway tier as pilot only | Now | Architecture owner | Preview status | 03 A16 | Open
03 Gateway | Counter key derived from validated identity | Now | Security | Identity design | 03 A4 | Open
03 Gateway | Tier and region per pursuit (capacity notices) | Before quote | CIS Infra | Region recheck | 03 A18 | Open
03 Gateway | Hard currency cap required or not | Customer approval | Customer budget owner | Overshoot tests | 03 A7 | Open
04 Capacity and FinOps | Assessment as fixed-fee entry offer | Now | Offering owner | Deck 04 | 04 exec 10 | Open
04 Capacity and FinOps | No commitment advice without measured data and customer prices | Now | CIS Infra leadership | Policy | 04 exec 10 | Open
04 Capacity and FinOps | Benchmark tooling and method | After pilot | AI tower lead | Pilot results | 04 D1 | Open
04 Capacity and FinOps | GPU proof-of-concept offer | Tower agreement | AI tower lead | Demand and skills | 04 D1 | Open
05 Managed Operations | Proposed packages for pilots | Now | Offering owner | Deck 05 | 05 exec 7 | Open
05 Managed Operations | No 24x7 without funded roster and escalation | Now | Delivery leadership | Policy | 05 exec 7 | Open
05 Managed Operations | Service objective values | After pilot | Delivery leadership with customer | Ticket data | 05 exec 8 | Open
05 Managed Operations | Security resolver model per customer | Per engagement | Customer CISO delegate | SOC contracts | 05 D1 | Open